## Action Plan
<Instructions: delete all material between < > characters, replace @@@ with relevant text, and fill in the table>
<Greyed out lines are for the 'Ref' and 'Name' of a set of activities only - no need to fill in other cells on the line.>
<'Outcome' is what you expect to be in place when the task is finished.>
<'Days' is the number of days effort required to perform the activity>
<'Start' and 'End' are dates eg. 01Feb>
<'Status' can be Open, Started or Done>
PawdocDP Preservation Plan CHART
This Chart has been designed to a) print A4 portrait without the 'Notes' column or Gantt chart.
b) be sorted by 'Start' or 'End' date, or 'Owner', and to be returned to its original order by sorting on 'Ref'.
<Insert preferred date ranges in cells below>
Ref | Activity Name | Outcome | Owner | Days | Start | End | Status | Notes | <@@@> | <@@@> | <@@@> | <@@@> | <@@@> | <@@@> | <@@@> | <eg. 02-08Feb> | <eg. 09-15Feb> | <eg. 16-22Feb>
1 | Export files from Fish Document Management System
1.1 | Backup Index & Fish config files | Backup on hard disk
1.2 | Convert '/' to '-' in all Ref Nos | No Ref Nos with '/'
1.3 | Obtain external hard drive (EHD) | EHD in study
1.4 | Backup Index and all Fish files | Full backup on EHD
1.5 | Export Fish files to flat files | Flat files in folders
1.6 | Do visual check of OL folders | No OL files left
1.7 | Do Filemaker vs folder files check | Completed checklist
2 | Adjust problem zip files
2.1 | Combine the 5 zips in 7951/01 | 1 zip file
2.2 | Convert visio files in 6771/02 | No Visio files in zip
2.3 | Convert to PDF (25 instances) | 25 new PDFs
2.4 | Convert to 11 separate base files | 11 separate files
2.5 | Fix some links and rezip | All links working
2.6 | Record need for future work (6) | Notes for Maint Plan
2.7 | Replace with updated file (2) | 2 replaced files
2.8 | Store as base files (218) | 218 separate files
2.9 | Do final check of Zip list | completed zip list
2.10 | Check Index for all zip list items | Completed checklist
3 | Adjust problem files identified by DROID
3.1 | Convert 16 htm files to PDF | 16 PDFs
3.2 | Change file extension (3) | One exe and 2 DLL files
3.3 | Check after total Fish export (1) | 1 working file
3.4 | Check rotation files (1613) | 1613 checked files
3.5 | Save in current Office vsn (336) | 336 updated files
3.6 | Convert Visio to PDF (5) | 5 PDF files
3.6 | Do final check of DROID doc | Completed Droid doc
3.5 | Check Index for all DROID items | Completed checklist
4 | Deal with files that won't open (FTWO)
4.1 | Convert 22 word files by Zamzar | 22 updated Word files
4.2 | Convert 155 ppt files by Zamzar | 155 updated PPTs
4.3 | Convert 6 Visio files by Zamzar | 6 PDF files
4.4 | Do final check of FTWO doc | Completed FTWO doc
4.5 | Check Index for all FTWO items | Completed checklist
5 | Deal with Physical Disks (PD)
5.1 | Include files after Fish Export (4) | 4 new files in folders
5.2 | Create zips of OL disks (38) | 38 zip files
5.3 | Create zips of 2008 backup (18) | 18 zip files
5.4 | Create zips of backup disks (70) | 70 zip files
5.5 | Update Index re zips with info (8) | Notes in 8 index entries
5.6 | Do final check of PD document | Completed PD doc
5.7 | Include all PD zips in Index | New index entries
5.8 | Check Index for all PD items | Completed checklist
6 | Deal with Double Unsorted (DU) files
6.1 | Sort PDF pages to correct order | Pages in right order
6.2 | Do final check of DU Index info | DU index checked-off
7 | Create Preservation Maintenance Plan (PMP)
7.1 | Define maintenance activities | Maintenance notes
7.2 | Document Maintenance Plan | Maintenance Plan
7.3 | Place reminders in calendar | Updated calendar
8 | Revise the Backup and DR arrangements
8.1 | Write Backup & DR document | Backup doc v0.1
8.2 | Initiate cloud backup | Replica in cloud
8.3 | Test cloud restore | Files in test area
8.4 | Initiate external HD backups | Replica on EHD
8.5 | Finalise the Backup & DR doc | Backup doc v1.0
9 | Produce User Guide (UG)
9.1 | Create User Guide | User Guide v0.1
9.2 | Insert Backup & DR doc in UG | User Guide v1.0
9.3 | Place user guide in Index | Doc in Index & folders
9.4 | Place user guide in boxes | Doc in boxes
10 | Close down PawdocDP project
10.1 | Do final check of folders/files | Adjusted folders/files
10.2 | Do final check of Index | Adjusted Index
10.3 | Finalise/store PawdocDP docs | Filed docs/closed folder
10.4 | Create full DVD backup | Populated DVDs
10.5 | Ship DVD backup to remote locale | DVDs in shipment
|  |  | Total | 0