## Action Plan
<'Status' can be Open, Started or Done>
<'Date Done' can be day/month eg. 23/7
PAWDOC 2021 Preservation Plan CHART
This Chart has been designed to a) print A4 portrait without the 'Notes' column or Gantt chart.
b) be sorted by 'Start' or 'End' date, or 'Owner', and to be returned to its original order by sorting on 'Ref'.
Ref | Activity Name | Outcome | Owner | Days | Start | End | Status | Date Done | Notes | 16-22Oct | 23-29Oct | 30Oct-05Nov | 06Nov-12Nov | 13Nov-19Nov | 20Nov-26Nov | 27Nov-03Dec
1 | Perform bulk conversions
1.1 | Convert 28 Help files to chm | 28 .chm files | PAW | 4 | 2021-10-17 | 2021-10-20 | Open
1.2 | Convert 317 Excel docs to xlsx | 317.xlsx files | PAW | 5 | 2021-10-21 | 2021-10-25 | Open
1.3 | Convert 974 Word docs to docx | 974 .docx files | PAW | 15 | 2021-10-25 | 2021-11-09 | Open
2 | Convert files using Zamzar
2.1 | Convert 3 Photoshop files | 3 .jpg files | PAW | 0.2 | 2021-11-06 | 2021-11-10
2.2 | Convert 1 Lotus Organiser file | 1 new file | PAW | 0.1 | 2021-11-06 | 2021-11-10
2.3 | Convert 4 Lotus ScreenCam files | 4 new files | PAW | 0.2 | 2021-11-06 | 2021-11-10
2.4 | Convert 28 Project files to xlsx | 28 .xlsx files | PAW | 1 | 2021-11-09 | 2021-11-10
2.5 | Convert 16 .DBF files to xlsx | 16 .xlsx files | PAW | 0.5 | 2021-11-11 | 2021-11-15
2.6 | Convert 168 Visio files to pptx | 168 .pptx files | PAW | 5 | 2021-11-11 | 2021-11-15
2.7 | Convert 13 Powerpoint files to pptx | 13 .pptx files | PAW | 1 | 2021-11-16 | 2021-11-17
3 | Update conversion records
3.1 | Perform Change Sheet Other Actions | Completed checklist | PAW | 2 | 2021-11-18 | 2021-11-19
3.2 | Write up Possible Future issues | Text for Maintenance Plan | PAW | 1 | 2021-11-20 | 2021-11-21
3.3 | Check index is correct for conversions | 3 completed checklists | PAW | 1 | 2021-11-22 | 2021-11-22
4 | Produce documentation
4.1 | Update the User Guide | User Guide v2.0 | PAW | 1.5 | 2021-11-23 | 2021-11-24
4.2 | Print the UG & put copy in archive box | UG v2.0 in archive box | PAW | 0.5 | 2021-11-25 | 2021-11-25
4.3 | Produce the next Maintenance Plan | New Maintenance Plan | PAW | 2 | 2021-11-26 | 2021-11-28
4.4 | Put date in preservation control sheet | Updated control sheet | PAW | 0.1 | 2021-11-28 | 2021-11-28
5 | Close down the Preservation Exercise
5.1 | Finalise PAWDOC DP2021 docs | v1.0 of all DP21 Docs | PAW | 1 | 2021-11-29 | 2021-11-30
5.2 | Place DP docs in PAWDOC | DP21 Docs in PAWDOC | PAW | 0.3 | 2021-11-30 | 2021-11-30
5.3 | Update PAWDOC local backup | New backup on Su's laptop | PAW | 0.3 | 2021-12-01 | 2021-12-01
5.4 | Update PAWDOC remote backup | New backup on Maxtor HD | PAW | 0.3 | 2021-12-01 | 2021-12-03
|  |  | Total | 42