## Action Plan
Preservation Plan Chart for SUPAUL-PHOTO Collection | [5 empty] | v1.0, 20Apr2015
Designed to a) print A4 portrait without Notes column or Gantt chart
b) be sorted by Start or End date, or Owner, and to be returned to original order by sorting on Ref
Ref | Activity | Outcome | Owner | Days | Start | End | Status | Notes | 20-26Apr | 27Apr-03May | 04May-10May | 11May-17May | 18May-24May | 25May-31May | 01Jun-07Jun | 08Jun-14Jun | 15Jun-21Jun | 22Jun-28Jun
1 | Convert Electronic File Formats
1.1 | Convert files | Converted files | PW | 1 | 2015-04-24 | 2015-04-26 | Open
1.2 | Run Droid and check formats | DROID results | PW | 1 | 2015-04-27 | 2015-04-27 | Open
1.3 | Update formats in Index | Updated Index doc | PW | 1 | 2015-04-28 | 2015-04-28 | Open
2 | Re-organise Folders and Files
2.1 | Create new folders/move files | New suite of folders | PW | 0.5 | 2015-04-29 | 2015-04-29 | Open
2.2 | Check for missing files | No missing files | PW | 1 | 2015-04-30 | 2015-05-03 | Open
2.3 | Check shortcuts and cross refs | Correct cross refs | PW | 0.5 | 2015-05-04 | 2015-05-05 | Open
3 | Check DVDs
3.1 | Ensure all videos are on DVDs | Complete set of DVDs | PW | 1 | 2015-05-16 | 2015-05-17 | Open
3.2 | Check DVD containers/labels | Correct DVD labels | PW | 0.5 | 2015-05-17 | 2015-05-17 | Open
4 | Revise Index and integrate it into the collection
4.1 | Define changes to Index | Index changes doc | PW | 1 | 2015-05-18 | 2015-05-19 | Open
4.2 | Modify the Index as defined | Updated Index layout | PW | 0.5 | 2015-05-20 | 2015-05-20 | Open
4.3 | Check Index contents | Correct Index contents | PW | 2 | 2015-05-21 | 2015-05-22 | Open
4.4 | Put Index file into MyPictures | Index in MyPictures | PW | 0.1 | 2015-05-22 | 2015-05-22 | Open
4.5 | Insert inter-component x-refs | X-refs in components | PW | 0.5 | 2015-05-23 | 2015-05-24 | Open
5 | Write user instructions
5.1 | Create draft user instructions | Draft instructions | PW | 1 | 2015-05-25 | 2015-05-26 | Open
5.2 | Get feedback on draft | Feedback notes | PW | 2 | 2015-05-28 | 2015-06-07 | Open
5.3 | Finalise user instructions | Final instruction doc | PW | 0.5 | 2015-06-08 | 2015-06-18 | Open
5.4 | Publish user instructions | Published instructions | PW | 0.2 | 2015-06-20 | 2015-06-21 | Open
6 | Create Preservation Maintenance Plan
6.1 | Define maintenance activities | Maintenance notes |  | 0.5 | 2015-06-08 | 2015-06-12 | Open
6.2 | Document Maintenance Plan | Maintenance Plan |  | 0.5 | 2015-06-13 | 2015-06-16 | Open
6.3 | Place reminders in calendar | Updated calendar |  | 0.1 | 2015-06-17 | 2015-06-18 | Open
7 | Revise the Backup and DR arrangements
7.1 | Obtain memory stick / SSD | Purchased stick/SSD |  | 0.2 | 2015-05-28 | 2015-06-07 | Open
7.2 | Write backup document | Backup doc |  | 1 | 2015-06-08 | 2015-06-18 | Open
7.3 | Check BT Cloud backups | Working BT Cloud |  | 0.2 | 2015-06-20 | 2015-06-20 | Open
7.4 | Test Cloud reinstatement | Correct process |  | 0.2 | 2015-06-20 | 2015-06-20 | Open
7.5 | Create DVD backups | Set of backups on DVD |  | 0.5 | 2015-06-21 | 2015-06-23 | Open
7.6 | Create backup on other laptop | Files on other vlapto |  | 1 | 2015-06-21 | 2015-06-23 | Open
7.7 | Test other laptop reinstatement | Correct process |  | 0.2 | 2015-06-21 | 2015-06-23 | Open
7.8 | Create external disk backup | Backup on ext disk |  | 0.3 | 2015-06-21 | 2015-06-23 | Open
7.9 | Test hard disk reinstatement | Correct process |  | 0.1 | 2015-06-21 | 2015-06-23 | Open
7.1 | Create mem stick/SSD backup | Backup on stick/SSD |  | 0.2 | 2015-06-21 | 2015-06-23 | Open
7.11 | Test stick/SSD reinstatement | Correct porocess |  | 0.1 | 2015-06-21 | 2015-06-23 | Open
7.12 | Ship backups to remote locales | Shipping planned |  | 0.1 | 2015-06-24 | 2015-06-24 | Open
7.13 | Ensure all backups are in place | Backups in place |  | 0.1 | 2015-06-24 | 2015-06-24 | Open
|  |  | Total | 19.6